## GANTT DIAGRAM
University Enrollment System
| Select the period to show advance | [7 empty] | Period Select | 84 |  |  | Plan duration | [5 empty] | Real Start |  |  |  | % Completed |  |  |  |  | Real (Out of plan) | [6 empty] | % Completed (Out of plan)
ID | ACTIVITY (WBS) | ITERATION | RESPONSIBLE | STORY POINTS | START DATE | DURATION | REAL START | REAL DURATION | PERCENTAGE COMPLETED | time axis 2025-09-15 to 2025-12-07
[10 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103
1 | PROJECT PROPOSAL AND PRESENTATION | 1 | All group |  | 1 | 14 | 1 | 14 | 100%
1,1 | Create a landing page for our website #1 | 1 | Marcelo | 3 | 1 | 10 | 1 | 14 | 100%
1,1,1 | Set up Django base project and directory structure |  | Marcelo |  | 1 | 2 | 1 | 3 | 100%
1,1,2 | Create base.html and index.html templates |  | Marcelo |  | 2 | 2 | 3 | 3 | 100%
1,1,3 | Add navigation bar with links to main pages |  | Marcelo |  | 4 | 2 | 6 | 3 | 100%
1,1,4 | Add CSS styling for layout and responsiveness |  | Marcelo |  | 6 | 2 | 9 | 3 | 100%
1,1,5 | Test that the page loads correctly and navigation works |  | Marcelo |  | 8 | 2 | 12 | 3 | 100%
1,2 | Proposal - Presentation #2 | 1 | All group | 2 | 13 | 5 | 13 | 5 | 100%
1,2,1 | Outline the main sections of the proposal (objectives, problem, motivation, features) |  | All group |  | 13 | 1 | 13 | 1 | 100%
1,2,2 | Design slide layout and visual style |  | All group |  | 14 | 1 | 14 | 1 | 100%
1,2,3 | Write concise bullet points and talking notes |  | All group |  | 15 | 1 | 15 | 1 | 100%
1,2,4 | Rehearse the presentation as a team |  | All group |  | 16 | 1 | 16 | 1 | 100%
1,2,5 | Submit the final slides to the instructor / TA |  | All group |  | 17 | 1 | 17 | 1 | 100%
1,3 | Proposal - Report #3 | 1 | All group | 2 | 11 | 4 | 11 | 4 | 100%
1,3,1 | Brainstorm and select a feasible project idea |  | All group |  | 11 | 0.5 | 11 | 0.5 | 100%
1,3,2 | Write the project proposal report following the given template |  | All group |  | 12 | 2 | 12 | 2 | 100%
1,3,3 | Review and finalize content as a team |  | All group |  | 13 | 1 | 13 | 1 | 100%
1,3,4 | Submit the report to the professor |  | All group |  | 14 | 0.5 | 14 | 0.5 | 100%
2 | REQUIREMENTS AND INITIAL PROJECT SETUP | 1 | All group |  | 15 | 14 | 15 | 14 | 100%
2,1 | Establish tasks and resposibles | 1 | All group |  | 15 | 9 | 15 | 9 | 100%
2,2 | Create program (landing) pages #4 | 2 | Afiya-Farjana | 5 | 26 | 9 | 26 | 17 | 100%
2,2,1 | Clone and set up the existing Django project from GitHub | 2 | Afiya-Farjana |  | 26 | 0.5 | 27 | 1 | 100%
2,2,2 | Design and integrate a custom university logo for consistent branding | 2 | Afiya-Farjana |  | 27 | 0.5 | 28 | 1 | 100%
2,2,3 | Add and style the navigation bar with active link highlighting using navbar.js | 2 | Afiya-Farjana |  | 28 | 1 | 29 | 2 | 100%
2,2,4 | Design and develop the main homepage, including a footer and embedded chatbox | 2 | Afiya-Farjana |  | 29 | 1.5 | 31 | 3 | 100%
2,2,5 | Create a dynamic admissions section using admission_sidebar.js to load pages (Graduate, Undergraduate, Online, Funding & Scholarships) without reloading | 2 | Afiya-Farjana |  | 30 | 1.5 | 34 | 3 | 100%
2,2,6 | Implement breadcrumbs to display navigation paths (e.g., Home / Admissions / Graduate) | 2 | Afiya-Farjana |  | 31 | 0.5 | 37 | 1 | 100%
2,2,7 | Develop and link additional pages (Faculty, Departments, Contact Us) through Django views and URLs | 2 | Afiya-Farjana |  | 32 | 1 | 38 | 2 | 100%
2,2,8 | Apply consistent responsive styling using style.css and admissions.css for a cohesive design | 2 | Afiya-Farjana |  | 33 | 1.5 | 40 | 3 | 100%
2,2,9 | Test and verify page loading, dynamic content switching, and navigation flow to ensure all integrated elements work smoothly together | 2 | Afiya-Farjana |  | 34 | 0.5 | 42 | 1 | 100%
2,3 | Create the rules-based chatbot #5 | 2 | Arnoldo | 4 | 26 | 14 | 26 | 14 | 100%
2,3,1 | Create chat layout | 2 | Arnoldo |  | 26 | 7 | 26 | 8 | 100%
2,3,2 | Add redirects to each program | 2 | Arnoldo |  | 33 | 7 | 34 | 9 | 100%
2,4 | Create a Gantt chart #6 | 2 | Jose | 2 | 36 | 4 | 36 | 4 | 100%
2,4,1 | Identify all project activities and deliverables from the proposal document | 2 | Jose |  | 36 | 1 | 36 | 1 | 100%
2,4,2 | Define each task’s start and end dates, duration, and dependencies | 2 | Jose |  | 37 | 1 | 37 | 1 | 100%
2,4,3 | Assign responsible members for each task | 2 | Jose |  | 38 | 1 | 38 | 1 | 100%
2,4,4 | Create the Gantt chart using Excel | 2 | Jose |  | 39 | 1 | 39 | 1 | 100%
2,5 | Create program pages #7 | 2 | Jannat | 3 | 28 | 9 | 28 | 12 | 100%
2,5,1 | Clone and set up the existing Django project from GitHub | 2 | Jannat |  | 28 | 1 | 28 | 1 | 100%
2,5,2 | Design a program page including the available programs, a sidebar including the list (Undergraduate, Graduate, Online Courses) | 2 | Jannat |  | 29 | 1 | 29 | 2 | 100%
2,5,3 | Create a sidebar for undergraduate, graduate, online courses section which are collapsible and are used to load pages (Undergraduate, Graduate, Online Courses) without reloading | 2 | Jannat |  | 30 | 2 | 31 | 2 | 100%
2,5,4 | Implement breadcrumbs to display navigation paths (e.g., Programs / Undergraduate / BSc in Computer Science) | 2 | Jannat |  | 32 | 1 | 33 | 1 | 100%
2,5,5 | Develop and link additional pages (Program Details) through Django views and URLs | 2 | Jannat |  | 33 | 1 | 34 | 2 | 100%
2,5,6 | Apply consistent responsive styling using pages.css and style.css for a cohesive design | 2 | Jannat |  | 34 | 2 | 36 | 2 | 100%
2,5,7 | Test and verify page loading, dynamic content navigation, and seamless flow through to ensure out all integrated elements | 2 | Jannat |  | 36 | 1 | 38 | 2 | 100%
2,6 | Create the user registration system #8 | 2 | Marcelo | 3 | 36 | 9 | 36 | 7 | 100%
2,6,1 | Set up of Authentication App inside Django, including Migrations and proper set up | 2 | Marcelo |  | 36 | 2 | 36 | 2 | 100%
2,6,2 | Creation of Administrator section and Superuser credentials | 2 | Marcelo |  | 38 | 1 | 38 | 1 | 100%
2,6,3 | Creation of Registration Form, along with UI changes and middleware set up | 2 | Marcelo |  | 39 | 2 | 39 | 2 | 100%
2,6,4 | Creation of Log In Form, along with UI changes and middleware set up | 2 | Marcelo |  | 41 | 2 | 41 | 1 | 100%
2,6,5 | Creation of Log Out Form, along with UI changes and middleware set up | 2 | Marcelo |  | 43 | 2 | 42 | 1 | 100%
3 | PROJECT PROGRESS REPORT | 2 | All group |  | 37 | 6 | 37 | 6 | 100%
3,1 | Progress Presentation #19 | 2 | All group | 2 | 37 | 3 | 37 | 3 | 100%
3,1,1 | Project Summary |  | All group |  | 37 | 3 | 37 | 3 | 100%
3,1,2 | Use Case diagram summarizing the features |  | All group |  | 37 | 3 | 37 | 3 | 100%
3,1,3 | Progress to Date |  | All group |  | 37 | 3 | 37 | 3 | 100%
3,1,4 | Challenges and Solutions |  | All group |  | 37 | 3 | 37 | 3 | 100%
3,1,5 | Next Steps |  | All group |  | 37 | 3 | 37 | 3 | 100%
3,2 | Progress Report #20 | 2 | All group | 1 | 40 | 3 | 40 | 3 | 100%
3,2,1 | Project Summary |  | All group |  | 40 | 3 | 40 | 3 | 100%
3,2,2 | Use Case diagram summarizing the features |  | All group |  | 40 | 3 | 40 | 3 | 100%
3,2,3 | Progress to Date |  | All group |  | 40 | 3 | 40 | 3 | 100%
3,2,4 | Challenges and Solutions |  | All group |  | 40 | 3 | 40 | 3 | 100%
3,2,5 | Next Steps |  | All group |  | 40 | 3 | 40 | 3 | 100%
4 | DEVELOPMENT AND INTEGRATION | 3 | All group |  | 39 | 46 | 39 | 46 | 100%
4,1 | Create the User Feedback System #12 | 3 | Nabil | 3 | 39 | 7 | 39 | 37 | 100%
4,1,1 | Set up the Django environment | 3 | Nabil |  | 39 | 0.5 | 39 | 6 | 100%
4,1,2 | Download and clone the existing project | 3 | Nabil |  | 39 | 0.5 | 45 | 6 | 100%
4,1,3 | Create the feedback input boxes utilizing Django forms | 3 | Nabil |  | 40 | 1 | 51 | 6 | 100%
4,1,4 | Connect to the database | 3 | Nabil |  | 41 | 1 | 57 | 6 | 100%
4,1,5 | Set up the feedback button in the navbar and match css styling to be consistent with the rest of the pages | 3 | Nabil |  | 42 | 2 | 63 | 6 | 100%
4,1,6 | Perform the unit and demo tests | 3 | Nabil |  | 44 | 2 | 69 | 7 | 100%
4,2 | Create chat transcript functionality for students #15 | 3 | Arnoldo | 5 | 41 | 5 | 41 | 5 | 100%
4,3 | Unit Test: Chatbot #16 | 3 | Jose | 3 | 41 | 6 | 55 | 6 | 100%
4,4 | Configure the project database #17 | 3 | Marcelo | 5 | 45 | 4 | 59 | 26 | 100%
4,4,1 | Create Program models | 3 | Marcelo |  | 45 | 1 | 59 | 9 | 100%
4,4,2 | Create User models | 3 | Marcelo |  | 46 | 1 | 68 | 9 | 100%
4,4,3 | Create signal to detect changes on users | 3 | Marcelo |  | 47 | 2 | 77 | 8 | 100%
4,5 | Create student enrollment system #18 | 3 | Marcelo | 5 | 47 | 16 | 61 | 24 | 100%
4,6 | Unit Test: Pages #27 | 3 | Selenge | 2 | 57 | 3 | 57 | 10 | 100%
4,7 | Unit Test: Users #28 | 3 | Arnoldo | 2 | 57 | 3 | 57 | 10 | 100%
4,8 | Convert Static Pages to Dynamic #30 | 3 | Afiya-Farjana | 5 | 63 | 1 | 67 | 7 | 100%
4,9 | Implement a professional development workflow #29 | 4 | Arnoldo | 7 | 58 | 15 | 58 | 27 | 100%
4,9,1 | Security & Secrets Management | 4 | Arnoldo |  | 58 | 4 | 58 | 5 | 100%
4,9,2 | Code Quality & Formatting | 4 | Arnoldo |  | 62 | 3 | 63 | 5 | 100%
4,9,3 | Pre-commit Hooks | 4 | Arnoldo |  | 65 | 2 | 68 | 5 | 100%
4,9,4 | CI Pipeline Integration | 4 | Arnoldo |  | 67 | 3 | 73 | 6 | 100%
4,9,5 | Architecture & Commit Standards | 4 | Arnoldo |  | 70 | 3 | 79 | 6 | 100%
4,10 | Create language switch #9 | 4 | Arnoldo | 3 | 61 | 10 | 58 | 10 | 100%
4,10,1 | Website Localization | 4 | Arnoldo |  | 61 | 5 | 58 | 5 | 100%
| Configure i18n in settings.py | 4 | Arnoldo |  | 61 | 1 | 59 | 1 | 100%
| Add LocaleMiddleware and update middleware order | 4 | Arnoldo |  | 62 | 0.5 | 60 | 0.5 | 100%
| Add language switch dropdown to navbar template | 4 | Arnoldo |  | 62 | 1 | 60 | 1 | 100%
| Use tags in all templates | 4 | Arnoldo |  | 63 | 1 | 61 | 1 | 100%
| Generate translation files | 4 | Arnoldo |  | 64 | 0.5 | 62 | 0.5 | 100%
| Translate English → Mongolian for static UI texts | 4 | Arnoldo |  | 65 | 1 | 62 | 1 | 100%
4,10,2 | Chatbot Localization | 4 | Arnoldo |  | 66 | 3 | 62 | 3 | 100%
| Read active language from cookie/session in chatbot endpoint | 4 | Arnoldo |  | 66 | 0.5 | 62 | 0.5 | 100%
| Implement language-aware rule-based chatbot logic | 4 | Arnoldo |  | 66 | 1 | 62 | 1 | 100%
| Add translation dictionary (MVP) for chatbot responses (English & Mongolian) | 4 | Arnoldo |  | 67 | 0.5 | 63 | 0.5 | 100%
| Return chatbot replies in the user’s selected language | 4 | Arnoldo |  | 67 | 0.5 | 63 | 0.5 | 100%
| Test chatbot responses in both languages | 4 | Arnoldo |  | 68 | 0.5 | 64 | 0.5 | 100%
4,10,3 | Testing | 4 | Arnoldo |  | 69 | 2 | 65 | 2 | 100%
| Verify language switch affects both website and chatbot | 4 | Arnoldo |  | 69 | 0.5 | 65 | 0.5 | 100%
| Write unit tests for language persistence and localized chatbot replies | 4 | Arnoldo |  | 70 | 0.5 | 65 | 0.5 | 100%
| Prepare demo steps and update documentation | 4 | Arnoldo |  | 70 | 0.5 | 66 | 0.5 | 100%
4,11 | Creating automatic resource delivery after registration #14 | 4 | Arnoldo | 3 | 70 | 3 | 75 | 8 | 100%
4,11,1 | Add email field to user registration form using a custom UserRegistrationForm | 4 | Arnoldo |  | 58 | 0.5 | 75 | 2 | 100%
4,11,2 | Update registration view to use the new form and validate email | 4 | Arnoldo |  | 58 | 0.5 | 77 | 1 | 100%
4,11,3 | Implement helper function to send welcome + admission resources email | 4 | Arnoldo |  | 59 | 0.5 | 78 | 1 | 100%
4,11,4 | Integrate email sending logic into the registration flow (trigger after successful registration) | 4 | Arnoldo |  | 59 | 0.5 | 79 | 2 | 100%
4,11,5 | Configure SMTP email backend using .env (Ethereal for dev) | 4 | Arnoldo |  | 60 | 0.5 | 81 | 1 | 100%
4,11,6 | Test email delivery + update E2E test to support new email field in registration flow | 4 | Arnoldo |  | 60 | 0.5 | 82 | 1 | 100%
4,12 | Unit test : Resource delivery #31 | 4 | Selenge | 2 | 73 | 3 | 73 | 10 | 100%
4,13 | Unit test: Localization #32 | 4 | Selenge | 2 | 73 | 3 | 73 | 11 | 100%
4,14 | Unit test: Feedback #33 | 4 | Selenge | 2 | 73 | 3 | 73 | 5 | 100%
4,15 | Send program resources via email upon request to the chatbot #35 | 4 | Arnoldo | 3 | 73 | 3 | 73 | 4 | 100%
4,15,1 | Create logic so that the student can navigate the chatbot to the email delivery option | 4 | Selenge |  | 67 | 0.5 | 73 | 1 | 100%
4,15,2 | Create email delivery logic on the Console Backend SMTP as a first test | 4 | Selenge |  | 67 | 0.5 | 74 | 1 | 100%
4,15,3 | Replace the console backend information with a SMTP mailbox sandbox service (ethereal.emai) | 4 | Selenge |  | 68 | 1 | 75 | 1 | 100%
4,15,4 | Ensure that no secret keys are exposed | 4 | Selenge |  | 69 | 1 | 76 | 1 | 100%
7 | REPORT | 5 | All group | 4 | 78 | 7 | 78 | 7 | 100%

## Sheet1
ID | ACTIVITY (WBS) | ITERATION | RESPONSIBLE | START DATE | DURATION | REAL START | REAL DURATION | % | BASE LINE | REAL | REAL GRAF
1,1,1 | Set up Django base project and directory structure |  | Marcelo | 1 | 2 | 1 | 3 | 100% | 3 | 4 | 11
1,1,2 | Create base.html and index.html templates |  | Marcelo | 2 | 2 | 3 | 3 | 100% | 4 | 6 | 11
1,1,3 | Add navigation bar with links to main pages |  | Marcelo | 4 | 2 | 6 | 3 | 100% | 6 | 9 | 11
1,3,1 | Brainstorm and select a feasible project idea |  | All group | 11 | 0.5 | 11 | 0.5 | 100% | 11.5 | 11.5 | 14
1,1,4 | Add CSS styling for layout and responsiveness |  | Marcelo | 6 | 2 | 9 | 3 | 100% | 8 | 12 | 11
1,2,1 | Outline the main sections of the proposal (objectives, problem, motivation, features) |  | All group | 13 | 1 | 13 | 1 | 100% | 14 | 14 | 11.5
1,3,2 | Write the project proposal report following the given template |  | All group | 12 | 2 | 12 | 2 | 100% | 14 | 14 | 14
1,3,3 | Review and finalize content as a team |  | All group | 13 | 1 | 13 | 1 | 100% | 14 | 14 | 14
1,3,4 | Submit the report to the professor |  | All group | 14 | 0.5 | 14 | 0.5 | 100% | 14.5 | 14.5 | 14.5
1,1,5 | Test that the page loads correctly and navigation works |  | Marcelo | 8 | 2 | 12 | 3 | 100% | 10 | 15 | 11
1,2,2 | Design slide layout and visual style |  | All group | 14 | 1 | 14 | 1 | 100% | 15 | 15 | 14
1,2,3 | Write concise bullet points and talking notes |  | All group | 15 | 1 | 15 | 1 | 100% | 16 | 16 | 14
1,2,4 | Rehearse the presentation as a team |  | All group | 16 | 1 | 16 | 1 | 100% | 17 | 17 | 14
1,2,5 | Submit the final slides to the instructor / TA |  | All group | 17 | 1 | 17 | 1 | 100% | 18 | 18 | 14
2,1 | Establish tasks and resposibles | 1 | All group | 15 | 9 | 15 | 9 | 100% | 24 | 24 | 24
2,2,1 | Clone and set up the existing Django project from GitHub | 2 | Afiya-Farjana | 26 | 0.5 | 27 | 1 | 100% | 26.5 | 28 | 28
2 | REQUIREMENTS AND INITIAL PROJECT SETUP | 1 | All group | 15 | 14 | 15 | 14 | 100% | 29 | 29 | 15
2,2,2 | Design and integrate a custom university logo for consistent branding | 2 | Afiya-Farjana | 27 | 0.5 | 28 | 1 | 100% | 27.5 | 29 | 29
2,5,1 | Clone and set up the existing Django project from GitHub | 2 | Jannat | 28 | 1 | 28 | 1 | 100% | 29 | 29 | 38
2,2,3 | Add and style the navigation bar with active link highlighting using navbar.js | 2 | Afiya-Farjana | 28 | 1 | 29 | 2 | 100% | 29 | 31 | 29
2,5,2 | Design a program page including the available programs, a sidebar including the list (Undergraduate, Graduate, Online Courses) | 2 | Jannat | 29 | 1 | 29 | 2 | 100% | 30 | 31 | 39
2,5,3 | Create a sidebar for undergraduate, graduate, online courses section which are collapsible and are used to load pages (Undergraduate, Graduate, Online Courses) without reloading | 2 | Jannat | 30 | 2 | 31 | 2 | 100% | 32 | 33 | 39
2,2,4 | Design and develop the main homepage, including a footer and embedded chatbox | 2 | Afiya-Farjana | 29 | 1.5 | 31 | 3 | 100% | 30.5 | 34 | 31
2,3,1 | Create chat layout | 2 | Arnoldo | 26 | 7 | 26 | 8 | 100% | 33 | 34 | 36
2,5,4 | Implement breadcrumbs to display navigation paths (e.g., Programs / Undergraduate / BSc in Computer Science) | 2 | Jannat | 32 | 1 | 33 | 1 | 0% | 33 | 34 | 39
2,5,5 | Develop and link additional pages (Program Details) through Django views and URLs | 2 | Jannat | 33 | 1 | 34 | 2 | 0% | 34 | 36 | 39
2,2,5 | Create a dynamic admissions section using admission_sidebar.js to load pages (Graduate, Undergraduate, Online, Funding & Scholarships) without reloading | 2 | Afiya-Farjana | 30 | 1.5 | 34 | 3 | 100% | 31.5 | 37 | 31
2,4,1 | Identify all project activities and deliverables from the proposal document | 2 | Jose | 36 | 1 | 36 | 1 | 100% | 37 | 37 | 37
2,2,6 | Implement breadcrumbs to display navigation paths (e.g., Home / Admissions / Graduate) | 2 | Afiya-Farjana | 31 | 0.5 | 37 | 1 | 100% | 31.5 | 38 | 33
2,4,2 | Define each task’s start and end dates, duration, and dependencies | 2 | Jose | 37 | 1 | 37 | 1 | 100% | 38 | 38 | 38
2,5,6 | Apply consistent responsive styling using pages.css and style.css for a cohesive design | 2 | Jannat | 34 | 2 | 36 | 2 | 100% | 36 | 38 | 40
2,6,1 | Set up of Authentication App inside Django, including Migrations and proper set up | 2 | Marcelo | 36 | 2 | 36 | 2 | 100% | 38 | 38 | 40
2,4,3 | Assign responsible members for each task | 2 | Jose | 38 | 1 | 38 | 1 | 100% | 39 | 39 | 38
2,6,2 | Creation of Administrator section and Superuser credentials | 2 | Marcelo | 38 | 1 | 38 | 1 | 100% | 39 | 39 | 40
2,2,7 | Develop and link additional pages (Faculty, Departments, Contact Us) through Django views and URLs | 2 | Afiya-Farjana | 32 | 1 | 38 | 2 | 100% | 33 | 40 | 34
2,4,4 | Create the Gantt chart using Excel | 2 | Jose | 39 | 1 | 39 | 1 | 100% | 40 | 40 | 38
2,5,7 | Test and verify page loading, dynamic content navigation, and seamless flow through to ensure out all integrated elements | 2 | Jannat | 36 | 1 | 38 | 2 | 100% | 37 | 40 | 40
3,1,1 | Project Summary |  | All group | 37 | 3 | 37 | 3 | 100% | 40 | 40 | 40
3,1,2 | Use Case diagram summarizing the features |  | All group | 37 | 3 | 37 | 3 | 0% | 40 | 40 | 40
3,1,3 | Progress to Date |  | All group | 37 | 3 | 37 | 3 | 100% | 40 | 40 | 41
3,1,4 | Challenges and Solutions |  | All group | 37 | 3 | 37 | 3 | 0% | 40 | 40 | 41
3,1,5 | Next Steps |  | All group | 37 | 3 | 37 | 3 | 100% | 40 | 40 | 42
2,6,3 | Creation of Registration Form, along with UI changes and middleware set up | 2 | Marcelo | 39 | 2 | 39 | 2 | 100% | 41 | 41 | 40
2,6,4 | Creation of Log In Form, along with UI changes and middleware set up | 2 | Marcelo | 41 | 2 | 41 | 1 | 100% | 43 | 42 | 40
2,2,8 | Apply consistent responsive styling using style.css and admissions.css for a cohesive design | 2 | Afiya-Farjana | 33 | 1.5 | 40 | 3 | 100% | 34.5 | 43 | 34
2,2,9 | Test and verify page loading, dynamic content switching, and navigation flow to ensure all integrated elements work smoothly together | 2 | Afiya-Farjana | 34 | 0.5 | 42 | 1 | 100% | 34.5 | 43 | 34
2,3,2 | Add redirects to each program | 2 | Arnoldo | 33 | 7 | 34 | 9 | 100% | 40 | 43 | 37
2,6,5 | Creation of Log Out Form, along with UI changes and middleware set up | 2 | Marcelo | 43 | 2 | 42 | 1 | 100% | 45 | 43 | 40
3,2,1 | Project Summary |  | All group | 40 | 3 | 40 | 3 | 0% | 43 | 43 | 42
3,2,2 | Use Case diagram summarizing the features |  | All group | 40 | 3 | 40 | 3 | 100% | 43 | 43 | 43
3,2,3 | Progress to Date |  | All group | 40 | 3 | 40 | 3 | 100% | 43 | 43 | 43
3,2,4 | Challenges and Solutions |  | All group | 40 | 3 | 40 | 3 | 100% | 43 | 43 | 43
3,2,5 | Next Steps |  | All group | 40 | 3 | 40 | 3 | 100% | 43 | 43 | 43
4,1,1 | Set up the Django environment | 3 | Nabil | 39 | 0.5 | 39 | 6 | 100% | 39.5 | 45 | 43
4,2 | Create chat transcript functionality for students #15 | 3 | Arnoldo | 41 | 5 | 41 | 5 | 0% | 46 | 46 | 45
4,1,2 | Download and clone the existing project | 3 | Nabil | 39 | 0.5 | 45 | 6 | 100% | 39.5 | 51 | 43
4,1,3 | Create the feedback input boxes utilizing Django forms | 3 | Nabil | 40 | 1 | 51 | 6 | 100% | 41 | 57 | 43
| Configure i18n in settings.py | 4 | Arnoldo | 61 | 1 | 59 | 1 | 0% | 62 | 60 | 62
| Add LocaleMiddleware and update middleware order | 4 | Arnoldo | 62 | 0.5 | 60 | 0.5 | 100% | 62.5 | 60.5 | 62
4,3 | Unit Test: Chatbot #16 | 3 | Jose | 41 | 6 | 55 | 6 | 100% | 47 | 61 | 46
| Add language switch dropdown to navbar template | 4 | Arnoldo | 62 | 1 | 60 | 1 | 0% | 63 | 61 | 62
| Use tags in all templates | 4 | Arnoldo | 63 | 1 | 61 | 1 | 100% | 64 | 62 | 62.5
| Generate translation files | 4 | Arnoldo | 64 | 0.5 | 62 | 0.5 | 100% | 64.5 | 62.5 | 63
| Read active language from cookie/session in chatbot endpoint | 4 | Arnoldo | 66 | 0.5 | 62 | 0.5 | 100% | 66.5 | 62.5 | 64
4,1,4 | Connect to the database | 3 | Nabil | 41 | 1 | 57 | 6 | 100% | 42 | 63 | 43
4,9,1 | Security & Secrets Management | 4 | Arnoldo | 58 | 4 | 58 | 5 | 0% | 62 | 63 | 62
| Translate English → Mongolian for static UI texts | 4 | Arnoldo | 65 | 1 | 62 | 1 | 0% | 66 | 63 | 63
| Implement language-aware rule-based chatbot logic | 4 | Arnoldo | 66 | 1 | 62 | 1 | 100% | 67 | 63 | 64.5
| Add translation dictionary (MVP) for chatbot responses (English & Mongolian) | 4 | Arnoldo | 67 | 0.5 | 63 | 0.5 | 0% | 67.5 | 63.5 | 65
| Return chatbot replies in the user’s selected language | 4 | Arnoldo | 67 | 0.5 | 63 | 0.5 | 100% | 67.5 | 63.5 | 66
| Test chatbot responses in both languages | 4 | Arnoldo | 68 | 0.5 | 64 | 0.5 | 0% | 68.5 | 64.5 | 66
| Verify language switch affects both website and chatbot | 4 | Arnoldo | 69 | 0.5 | 65 | 0.5 | 0% | 69.5 | 65.5 | 66
| Write unit tests for language persistence and localized chatbot replies | 4 | Arnoldo | 70 | 0.5 | 65 | 0.5 | 0% | 70.5 | 65.5 | 67
| Prepare demo steps and update documentation | 4 | Arnoldo | 70 | 0.5 | 66 | 0.5 | 0% | 70.5 | 66.5 | 67
4,6 | Unit Test: Pages #27 | 3 | Selenge | 57 | 3 | 57 | 10 | 0% | 60 | 67 | 58
4,7 | Unit Test: Users #28 | 3 | Arnoldo | 57 | 3 | 57 | 10 | 0% | 60 | 67 | 60
4,4,1 | Create Program models | 3 | Marcelo | 45 | 1 | 59 | 9 | 0% | 46 | 68 | 46
4,9,2 | Code Quality & Formatting | 4 | Arnoldo | 62 | 3 | 63 | 5 | 0% | 65 | 68 | 65
4,1,5 | Set up the feedback button in the navbar and match css styling to be consistent with the rest of the pages | 3 | Nabil | 42 | 2 | 63 | 6 | 100% | 44 | 69 | 43
4,9,3 | Pre-commit Hooks | 4 | Arnoldo | 65 | 2 | 68 | 5 | 100% | 67 | 73 | 60
4,8 | Convert Static Pages to Dynamic #30 | 3 | Afiya-Farjana | 63 | 1 | 67 | 7 | 0% | 64 | 74 | 64
4,15,1 | Create logic so that the student can navigate the chatbot to the email delivery option | 4 | Selenge | 67 | 0.5 | 73 | 1 | 0% | 67.5 | 74 | 67.5
4,15,2 | Create email delivery logic on the Console Backend SMTP as a first test | 4 | Selenge | 67 | 0.5 | 74 | 1 | 0% | 67.5 | 75 | 67.5
4,1,6 | Perform the unit and demo tests | 3 | Nabil | 44 | 2 | 69 | 7 | 0% | 46 | 76 | 44
4,15,3 | Replace the console backend information with a SMTP mailbox sandbox service (ethereal.emai) | 4 | Selenge | 68 | 1 | 75 | 1 | 0% | 69 | 76 | 69
4,4,2 | Create User models | 3 | Marcelo | 46 | 1 | 68 | 9 | 100% | 47 | 77 | 47
4,11,1 | Add email field to user registration form using a custom UserRegistrationForm | 4 | Arnoldo | 58 | 0.5 | 75 | 2 | 0% | 58.5 | 77 | 67
4,15,4 | Ensure that no secret keys are exposed | 4 | Selenge | 69 | 1 | 76 | 1 | 0% | 70 | 77 | 70
4,11,2 | Update registration view to use the new form and validate email | 4 | Arnoldo | 58 | 0.5 | 77 | 1 | 0% | 58.5 | 78 | 58.5
4,14 | Unit test: Feedback #33 | 4 | Selenge | 73 | 3 | 73 | 5 | 0% | 76 | 78 | 76
4,9,4 | CI Pipeline Integration | 4 | Arnoldo | 67 | 3 | 73 | 6 | 100% | 70 | 79 | 60
4,11,3 | Implement helper function to send welcome + admission resources email | 4 | Arnoldo | 59 | 0.5 | 78 | 1 | 0% | 59.5 | 79 | 59.5
4,11,4 | Integrate email sending logic into the registration flow (trigger after successful registration) | 4 | Arnoldo | 59 | 0.5 | 79 | 2 | 0% | 59.5 | 81 | 59.5
4,11,5 | Configure SMTP email backend using .env (Ethereal for dev) | 4 | Arnoldo | 60 | 0.5 | 81 | 1 | 0% | 60.5 | 82 | 60.5
4,11,6 | Test email delivery + update E2E test to support new email field in registration flow | 4 | Arnoldo | 60 | 0.5 | 82 | 1 | 0% | 60.5 | 83 | 60.5
4,12 | Unit test : Resource delivery #31 | 4 | Selenge | 73 | 3 | 73 | 10 | 0% | 76 | 83 | 76
4,13 | Unit test: Localization #32 | 4 | Selenge | 73 | 3 | 73 | 11 | 0% | 76 | 84 | 76
4,4,3 | Create signal to detect changes on users | 3 | Marcelo | 47 | 2 | 77 | 8 | 0% | 49 | 85 | 47
4,5 | Create student enrollment system #18 | 3 | Marcelo | 47 | 16 | 61 | 24 | 0% | 63 | 85 | 47
4,9,5 | Architecture & Commit Standards | 4 | Arnoldo | 70 | 3 | 79 | 6 | 0% | 73 | 85 | 73
7 | REPORT | 5 | All group | 78 | 7 | 78 | 7 | 0% | 85 | 85 | 85

## Sheet2
1,1,1 | Set up Django base project and directory structure |  | Marcelo | 1 | 2 | 1 | 3
1,1,2 | Create base.html and index.html templates |  | Marcelo | 2 | 2 | 3 | 3
1,1,3 | Add navigation bar with links to main pages |  | Marcelo | 4 | 2 | 6 | 3
1,1,4 | Add CSS styling for layout and responsiveness |  | Marcelo | 6 | 2 | 9 | 3
1,1,5 | Test that the page loads correctly and navigation works |  | Marcelo | 8 | 2 | 12 | 3
1,2,1 | Outline the main sections of the proposal (objectives, problem, motivation, features) |  | All group | 13 | 1 | 13 | 1
1,2,2 | Design slide layout and visual style |  | All group | 14 | 1 | 14 | 1
1,2,3 | Write concise bullet points and talking notes |  | All group | 15 | 1 | 15 | 1
1,2,4 | Rehearse the presentation as a team |  | All group | 16 | 1 | 16 | 1
1,2,5 | Submit the final slides to the instructor / TA |  | All group | 17 | 1 | 17 | 1
1,3,1 | Brainstorm and select a feasible project idea |  | All group | 11 | 0.5 | 11 | 0.5
1,3,2 | Write the project proposal report following the given template |  | All group | 12 | 2 | 12 | 2
1,3,3 | Review and finalize content as a team |  | All group | 13 | 1 | 13 | 1
1,3,4 | Submit the report to the professor |  | All group | 14 | 0.5 | 14 | 0.5
2 | REQUIREMENTS AND INITIAL PROJECT SETUP | 1 | All group | #REF! | 14 | 15 | 14
2,1 | Establish tasks and resposibles | 1 | All group | 15 | 9 | 15 | 9
2,2,1 | Clone and set up the existing Django project from GitHub | 2 | Afiya-Farjana | 26 | 0.5 | 27 | 1
2,2,2 | Design and integrate a custom university logo for consistent branding | 2 | Afiya-Farjana | 27 | 0.5 | 28 | 1
2,2,3 | Add and style the navigation bar with active link highlighting using navbar.js | 2 | Afiya-Farjana | 28 | 1 | 29 | 2
2,2,4 | Design and develop the main homepage, including a footer and embedded chatbox | 2 | Afiya-Farjana | 29 | 1.5 | 31 | 3
2,2,5 | Create a dynamic admissions section using admission_sidebar.js to load pages (Graduate, Undergraduate, Online, Funding & Scholarships) without reloading | 2 | Afiya-Farjana | 30 | 1.5 | 34 | 3
2,2,6 | Implement breadcrumbs to display navigation paths (e.g., Home / Admissions / Graduate) | 2 | Afiya-Farjana | 31 | 0.5 | 37 | 1
2,2,7 | Develop and link additional pages (Faculty, Departments, Contact Us) through Django views and URLs | 2 | Afiya-Farjana | 32 | 1 | 38 | 2
2,2,8 | Apply consistent responsive styling using style.css and admissions.css for a cohesive design | 2 | Afiya-Farjana | 33 | 1.5 | 40 | 3
2,2,9 | Test and verify page loading, dynamic content switching, and navigation flow to ensure all integrated elements work smoothly together | 2 | Afiya-Farjana | 34 | 0.5 | 42 | 1
2,3,1 | Create chat layout | 2 | Arnoldo | 26 | 7 | 26 | 8
2,3,2 | Add redirects to each program | 2 | Arnoldo | 33 | 7 | 34 | 9
2,4,1 | Identify all project activities and deliverables from the proposal document | 2 | Jose | 36 | 1 | 36 | 1
2,4,2 | Define each task’s start and end dates, duration, and dependencies | 2 | Jose | 37 | 1 | 37 | 1
2,4,3 | Assign responsible members for each task | 2 | Jose | 38 | 1 | 38 | 1
2,4,4 | Create the Gantt chart using Excel | 2 | Jose | 39 | 1 | 39 | 1
2,5,1 | Clone and set up the existing Django project from GitHub | 2 | Jannat | 28 | 1 | 28 | 1
2,5,2 | Design a program page including the available programs, a sidebar including the list (Undergraduate, Graduate, Online Courses) | 2 | Jannat | 29 | 1 | 29 | 2
2,5,3 | Create a sidebar for undergraduate, graduate, online courses section which are collapsible and are used to load pages (Undergraduate, Graduate, Online Courses) without reloading | 2 | Jannat | 30 | 2 | 31 | 2
2,5,4 | Implement breadcrumbs to display navigation paths (e.g., Programs / Undergraduate / BSc in Computer Science) | 2 | Jannat | 32 | 1 | 33 | 1
2,5,5 | Develop and link additional pages (Program Details) through Django views and URLs | 2 | Jannat | 33 | 1 | 34 | 2
2,5,6 | Apply consistent responsive styling using pages.css and style.css for a cohesive design | 2 | Jannat | 34 | 2 | 36 | 2
2,5,7 | Test and verify page loading, dynamic content navigation, and seamless flow through to ensure out all integrated elements | 2 | Jannat | 36 | 1 | 38 | 2
2,6,1 | Set up of Authentication App inside Django, including Migrations and proper set up | 2 | Marcelo | 36 | 2 | 36 | 2
2,6,2 | Creation of Administrator section and Superuser credentials | 2 | Marcelo | 38 | 1 | 38 | 1
2,6,3 | Creation of Registration Form, along with UI changes and middleware set up | 2 | Marcelo | 39 | 2 | 39 | 2
2,6,4 | Creation of Log In Form, along with UI changes and middleware set up | 2 | Marcelo | 41 | 2 | 41 | 1
2,6,5 | Creation of Log Out Form, along with UI changes and middleware set up | 2 | Marcelo | 43 | 2 | 42 | 1
3,1,1 | Project Summary |  | All group | 37 | 3 | 37 | 3
3,1,2 | Use Case diagram summarizing the features |  | All group | 37 | 3 | 37 | 3
3,1,3 | Progress to Date |  | All group | 37 | 3 | 37 | 3
3,1,4 | Challenges and Solutions |  | All group | 37 | 3 | 37 | 3
3,1,5 | Next Steps |  | All group | 37 | 3 | 37 | 3
3,2,1 | Project Summary |  | All group | 40 | 3 | 40 | 3
3,2,2 | Use Case diagram summarizing the features |  | All group | 40 | 3 | 40 | 3
3,2,3 | Progress to Date |  | All group | 40 | 3 | 40 | 3
3,2,4 | Challenges and Solutions |  | All group | 40 | 3 | 40 | 3
3,2,5 | Next Steps |  | All group | 40 | 3 | 40 | 3
4,1,1 | Set up the Django environment | 3 | Nabil | 39 | 0.5 | 39 | 6
4,1,2 | Download and clone the existing project | 3 | Nabil | 39 | 0.5 | 45 | 6
4,1,3 | Create the feedback input boxes utilizing Django forms | 3 | Nabil | 40 | 1 | 51 | 6
4,1,4 | Connect to the database | 3 | Nabil | 41 | 1 | 57 | 6
4,1,5 | Set up the feedback button in the navbar and match css styling to be consistent with the rest of the pages | 3 | Nabil | 42 | 2 | 63 | 6
4,1,6 | Perform the unit and demo tests | 3 | Nabil | 44 | 2 | 69 | 7
4,2 | Create chat transcript functionality for students #15 | 3 | Arnoldo | 41 | 5 | 41 | 5
4,3 | Unit Test: Chatbot #16 | 3 | Jose | 41 | 6 | 55 | 6
4,4,1 | Create Program models | 3 | Marcelo | 45 | 1 | 59 | 9
4,4,2 | Create User models | 3 | Marcelo | 46 | 1 | 68 | 9
4,4,3 | Create signal to detect changes on users | 3 | Marcelo | 47 | 2 | 77 | 8
4,5 | Create student enrollment system #18 | 3 | Marcelo | 47 | 16 | 61 | 24
4,6 | Unit Test: Pages #27 | 3 | Selenge | 57 | 3 | 57 | 10
4,7 | Unit Test: Users #28 | 3 | Arnoldo | 57 | 3 | 57 | 10
4,8 | Convert Static Pages to Dynamic #30 | 3 | Afiya-Farjana | 63 | 1 | 67 | 7
4,9,1 | Security & Secrets Management | 4 | Arnoldo | 58 | 4 | 58 | 5
4,9,2 | Code Quality & Formatting | 4 | Arnoldo | 62 | 3 | 63 | 5
4,9,3 | Pre-commit Hooks | 4 | Arnoldo | 65 | 2 | 68 | 5
4,9,4 | CI Pipeline Integration | 4 | Arnoldo | 67 | 3 | 73 | 6
4,9,5 | Architecture & Commit Standards | 4 | Arnoldo | 70 | 3 | 79 | 6
| Configure i18n in settings.py | 4 | Arnoldo | 61 | 1 | 59 | 1
| Add LocaleMiddleware and update middleware order | 4 | Arnoldo | 62 | 0.5 | 60 | 0.5
| Add language switch dropdown to navbar template | 4 | Arnoldo | 62 | 1 | 60 | 1
| Use tags in all templates | 4 | Arnoldo | 63 | 1 | 61 | 1
| Generate translation files | 4 | Arnoldo | 64 | 0.5 | 62 | 0.5
| Translate English → Mongolian for static UI texts | 4 | Arnoldo | 65 | 1 | 62 | 1
| Read active language from cookie/session in chatbot endpoint | 4 | Arnoldo | 66 | 0.5 | 62 | 0.5
| Implement language-aware rule-based chatbot logic | 4 | Arnoldo | 66 | 1 | 62 | 1
| Add translation dictionary (MVP) for chatbot responses (English & Mongolian) | 4 | Arnoldo | 67 | 0.5 | 63 | 0.5
| Return chatbot replies in the user’s selected language | 4 | Arnoldo | 67 | 0.5 | 63 | 0.5
| Test chatbot responses in both languages | 4 | Arnoldo | 68 | 0.5 | 64 | 0.5
| Verify language switch affects both website and chatbot | 4 | Arnoldo | 69 | 0.5 | 65 | 0.5
| Write unit tests for language persistence and localized chatbot replies | 4 | Arnoldo | 70 | 0.5 | 65 | 0.5
| Prepare demo steps and update documentation | 4 | Arnoldo | 70 | 0.5 | 66 | 0.5
4,11,1 | Add email field to user registration form using a custom UserRegistrationForm | 4 | Arnoldo | 58 | 0.5 | 75 | 2
4,11,2 | Update registration view to use the new form and validate email | 4 | Arnoldo | 58 | 0.5 | 77 | 1
4,11,3 | Implement helper function to send welcome + admission resources email | 4 | Arnoldo | 59 | 0.5 | 78 | 1
4,11,4 | Integrate email sending logic into the registration flow (trigger after successful registration) | 4 | Arnoldo | 59 | 0.5 | 79 | 2
4,11,5 | Configure SMTP email backend using .env (Ethereal for dev) | 4 | Arnoldo | 60 | 0.5 | 81 | 1
4,11,6 | Test email delivery + update E2E test to support new email field in registration flow | 4 | Arnoldo | 60 | 0.5 | 82 | 1
4,12 | Unit test : Resource delivery #31 | 4 | Selenge | 73 | 3 | 73 | 10
4,13 | Unit test: Localization #32 | 4 | Selenge | 73 | 3 | 73 | 11
4,14 | Unit test: Feedback #33 | 4 | Selenge | 73 | 3 | 73 | 5
4,15,1 | Create logic so that the student can navigate the chatbot to the email delivery option | 4 | Selenge | 67 | 0.5 | 73 | 1
4,15,2 | Create email delivery logic on the Console Backend SMTP as a first test | 4 | Selenge | 67 | 0.5 | 74 | 1
4,15,3 | Replace the console backend information with a SMTP mailbox sandbox service (ethereal.emai) | 4 | Selenge | 68 | 1 | 75 | 1
4,15,4 | Ensure that no secret keys are exposed | 4 | Selenge | 69 | 1 | 76 | 1
7 | REPORT | 5 | All group | 78 | 7 | 78 | 7

## Burndown
DAY | TASK BL | TASK REAL | DAILY TASK | Base Line | Real | Completed %
1 | 0 | 0 | 0 | 101 | 101 | 0%
2 | 0 | 0 | 0 | 101 | 101 | 0%
3 | 0 | 0 | 0 | 101 | 101 | 0%
4 | 0 | 1 | 1 | 101 | 100 | 0.9901%
5 | 0 | 1 | 0 | 101 | 100 | 0.9901%
6 | 0 | 2 | 1 | 101 | 99 | 1.98%
7 | 0 | 2 | 0 | 101 | 99 | 1.98%
8 | 0 | 2 | 0 | 101 | 99 | 1.98%
9 | 0 | 3 | 1 | 101 | 98 | 2.97%
10 | 0 | 3 | 0 | 101 | 98 | 2.97%
11 | 5 | 4 | 1 | 96 | 97 | 3.96%
12 | 6 | 5 | 1 | 95 | 96 | 4.95%
13 | 6 | 5 | 0 | 95 | 96 | 4.95%
14 | 13 | 9 | 4 | 88 | 92 | 8.911%
15 | 15 | 11 | 2 | 86 | 90 | 10.89%
16 | 15 | 12 | 1 | 86 | 89 | 11.88%
17 | 15 | 13 | 1 | 86 | 88 | 12.87%
18 | 15 | 14 | 1 | 86 | 87 | 13.86%
19 | 15 | 14 | 0 | 86 | 87 | 13.86%
20 | 15 | 14 | 0 | 86 | 87 | 13.86%
21 | 15 | 14 | 0 | 86 | 87 | 13.86%
22 | 15 | 14 | 0 | 86 | 87 | 13.86%
23 | 15 | 14 | 0 | 86 | 87 | 13.86%
24 | 16 | 15 | 1 | 85 | 86 | 14.85%
25 | 16 | 15 | 0 | 85 | 86 | 14.85%
26 | 16 | 15 | 0 | 85 | 86 | 14.85%
27 | 17 | 15 | 0 | 84 | 86 | 14.85%
28 | 18 | 16 | 1 | 83 | 85 | 15.84%
29 | 20 | 19 | 3 | 81 | 82 | 18.81%
30 | 21 | 19 | 0 | 80 | 82 | 18.81%
31 | 22 | 21 | 2 | 79 | 80 | 20.79%
32 | 25 | 21 | 0 | 76 | 80 | 20.79%
33 | 28 | 22 | 1 | 73 | 79 | 21.78%
34 | 29 | 25 | 3 | 72 | 76 | 24.75%
35 | 31 | 25 | 0 | 70 | 76 | 24.75%
36 | 32 | 26 | 1 | 69 | 75 | 25.74%
37 | 34 | 28 | 2 | 67 | 73 | 27.72%
38 | 36 | 32 | 4 | 65 | 69 | 31.68%
39 | 38 | 34 | 2 | 63 | 67 | 33.66%
40 | 47 | 42 | 8 | 54 | 59 | 41.58%
41 | 49 | 43 | 1 | 52 | 58 | 42.57%
42 | 50 | 44 | 1 | 51 | 57 | 43.56%
43 | 56 | 53 | 9 | 45 | 48 | 52.48%
44 | 57 | 53 | 0 | 44 | 48 | 52.48%
45 | 58 | 54 | 1 | 43 | 47 | 53.47%
46 | 61 | 55 | 1 | 40 | 46 | 54.46%
47 | 63 | 55 | 0 | 38 | 46 | 54.46%
48 | 63 | 55 | 0 | 38 | 46 | 54.46%
49 | 64 | 55 | 0 | 37 | 46 | 54.46%
50 | 64 | 55 | 0 | 37 | 46 | 54.46%
51 | 64 | 56 | 1 | 37 | 45 | 55.45%
52 | 64 | 56 | 0 | 37 | 45 | 55.45%
53 | 64 | 56 | 0 | 37 | 45 | 55.45%
54 | 64 | 56 | 0 | 37 | 45 | 55.45%
55 | 64 | 56 | 0 | 37 | 45 | 55.45%
56 | 64 | 56 | 0 | 37 | 45 | 55.45%
57 | 64 | 57 | 1 | 37 | 44 | 56.44%
58 | 64 | 57 | 0 | 37 | 44 | 56.44%
59 | 66 | 57 | 0 | 35 | 44 | 56.44%
60 | 70 | 59 | 2 | 31 | 42 | 58.42%
61 | 72 | 61 | 2 | 29 | 40 | 60.4%
62 | 74 | 64 | 3 | 27 | 37 | 63.37%
63 | 77 | 70 | 6 | 24 | 31 | 69.31%
64 | 79 | 71 | 1 | 22 | 30 | 70.3%
65 | 81 | 73 | 2 | 20 | 28 | 72.28%
66 | 82 | 74 | 1 | 19 | 27 | 73.27%
67 | 85 | 76 | 2 | 16 | 25 | 75.25%
68 | 89 | 78 | 2 | 12 | 23 | 77.23%
69 | 91 | 79 | 1 | 10 | 22 | 78.22%
70 | 94 | 79 | 0 | 7 | 22 | 78.22%
71 | 96 | 79 | 0 | 5 | 22 | 78.22%
72 | 96 | 79 | 0 | 5 | 22 | 78.22%
73 | 97 | 80 | 1 | 4 | 21 | 79.21%
74 | 97 | 82 | 2 | 4 | 19 | 81.19%
75 | 97 | 83 | 1 | 4 | 18 | 82.18%
76 | 100 | 85 | 2 | 1 | 16 | 84.16%
77 | 100 | 88 | 3 | 1 | 13 | 87.13%
78 | 100 | 90 | 2 | 1 | 11 | 89.11%
79 | 100 | 92 | 2 | 1 | 9 | 91.09%
80 | 100 | 92 | 0 | 1 | 9 | 91.09%
81 | 100 | 93 | 1 | 1 | 8 | 92.08%
82 | 100 | 94 | 1 | 1 | 7 | 93.07%
83 | 100 | 96 | 2 | 1 | 5 | 95.05%
84 | 100 | 97 | 1 | 1 | 4 | 96.04%
85 | 102 | 101 | 4 | 0 | 0 | 100%