## GANTT DIAGRAM
University Enrollment System
| Select the period to show advance | [6 empty] | Period Select | 42 |  |  | Plan duration | [5 empty] | Real Start |  |  |  | % Completed |  |  |  |  | Real (Out of plan) | [6 empty] | % Completed (Out of plan)
ID | ACTIVITY (WBS) | ITERATION | RESPONSIBLE | START DATE | DURATION | REAL START | REAL DURATION | PERCENTAJGE COMPLETED | time axis 2025-09-15 to 2025-12-07
[93 empty] | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | time axis 2025-09-15 to 2025-12-07
1 | PROJECT PROPOSAL AND PRESENTATION | 1 | All group | 1 | 14 | 1 | 14 | 100%
1,1 | Create a landing page for our website #1 | 1 | Marcelo | 1 | 10 | 1 | 18 | 100%
1,1,1 | Set up Django base project and directory structure |  | Marcelo | 1 | 10 | 1 | 10 | 100%
1,1,2 | Create base.html and index.html templates |  | Marcelo | 1 | 10 | 1 | 10 | 100%
1,1,3 | Add navigation bar with links to main pages |  | Marcelo | 1 | 10 | 1 | 10 | 100%
1,1,4 | Add CSS styling for layout and responsiveness |  | Marcelo | 1 | 10 | 1 | 10 | 100%
1,1,5 | Test that the page loads correctly and navigation works |  | Marcelo | 1 | 10 | 1 | 10 | 100%
1,2 | Proposal - Presentation #2 | 1 | All group | 4 | 5 | 4 | 5 | 100%
1,2,1 | Outline the main sections of the proposal (objectives, problem, motivation, features) |  | All group | 13 | 1 | 13 | 1 | 100%
1,2,2 | Design slide layout and visual style |  | All group | 13 | 1 | 13 | 1 | 100%
1,2,3 | Write concise bullet points and talking notes |  | All group | 13 | 1 | 13 | 1 | 100%
1,2,4 | Rehearse the presentation as a team |  | All group | 13 | 1 | 13 | 1 | 100%
1,2,5 | Submit the final slides to the instructor / TA |  | All group | 13 | 1 | 13 | 1 | 100%
1,3 | Proposal - Report #3 | 1 | All group | 8 | 4 | 8 | 4 | 100%
1,3,1 | Brainstorm and select a feasible project idea |  | All group | 11 | 0.5 | 11 | 0.5 | 100%
1,3,2 | Write the project proposal report following the given template |  | All group | 12 | 2 | 12 | 2 | 100%
1,3,3 | Review and finalize content as a team |  | All group | 13 | 1 | 13 | 1 | 100%
1,3,4 | Submit the report to the professor |  | All group | 14 | 0.5 | 14 | 0.5 | 100%
2 | REQUIREMENTS AND INITIAL PROJECT SETUP | 1 | All group | 15 | 14 | 15 | 14 | 100%
2,1 | Establish tasks and resposibles | 1 | All group | 15 | 9 | 15 | 9 | 100%
2,2 | Create program (landing) pages #4 | 2 | Afiya-Farjana | 26 | 9 | 26 | 17 | 100%
2,2,1 | Clone and set up the existing Django project from GitHub | 2 | Afiya-Farjana | 26 | 0.5 | 27 | 1 | 100%
2,2,2 | Design and integrate a custom university logo for consistent branding | 2 | Afiya-Farjana | 27 | 0.5 | 28 | 1 | 100%
2,2,3 | Add and style the navigation bar with active link highlighting using navbar.js | 2 | Afiya-Farjana | 28 | 1 | 29 | 2 | 100%
2,2,4 | Design and develop the main homepage, including a footer and embedded chatbox | 2 | Afiya-Farjana | 29 | 1.5 | 31 | 3 | 100%
2,2,5 | Create a dynamic admissions section using admission_sidebar.js to load pages (Graduate, Undergraduate, Online, Funding & Scholarships) without reloading | 2 | Afiya-Farjana | 30 | 1.5 | 34 | 3 | 100%
2,2,6 | Implement breadcrumbs to display navigation paths (e.g., Home / Admissions / Graduate) | 2 | Afiya-Farjana | 31 | 0.5 | 37 | 1 | 100%
2,2,7 | Develop and link additional pages (Faculty, Departments, Contact Us) through Django views and URLs | 2 | Afiya-Farjana | 32 | 1 | 38 | 2 | 100%
2,2,8 | Apply consistent responsive styling using style.css and admissions.css for a cohesive design | 2 | Afiya-Farjana | 33 | 1.5 | 40 | 3 | 100%
2,2,9 | Test and verify page loading, dynamic content switching, and navigation flow to ensure all integrated elements work smoothly together | 2 | Afiya-Farjana | 34 | 0.5 | 42 | 1 | 100%
2,3 | Create the rules-based chatbot #5 | 2 | Arnoldo | 26 | 14 | 26 | 14 | 100%
2,3,1 | Create chat layout | 2 | Arnoldo | 26 | 7 | 26 | 8 | 100%
2,3,2 | Add redirects to each program | 2 | Arnoldo | 33 | 7 | 34 | 9 | 100%
2,4 | Create a Gantt chart #6 | 2 | Jose | 36 | 4 | 36 | 4 | 100%
2,4,1 | Identify all project activities and deliverables from the proposal document | 2 | Jose | 36 | 1 | 36 | 1 | 100%
2,4,2 | Define each task’s start and end dates, duration, and dependencies | 2 | Jose | 37 | 1 | 37 | 1 | 100%
2,4,3 | Assign responsible members for each task | 2 | Jose | 38 | 1 | 38 | 1 | 100%
2,4,4 | Create the Gantt chart using Excel | 2 | Jose | 39 | 1 | 39 | 1 | 100%
2,5 | Create program pages #7 | 2 | Jannat | 28 | 9 | 28 | 12 | 100%
2,5,1 | Clone and set up the existing Django project from GitHub | 2 | Jannat | 28 | 1 | 28 | 1 | 100%
2,5,2 | Design a program page including the available programs, a sidebar including the list (Undergraduate, Graduate, Online Courses) | 2 | Jannat | 29 | 1 | 29 | 2 | 100%
2,5,3 | Create a sidebar for undergraduate, graduate, online courses section which are collapsible and are used to load pages (Undergraduate, Graduate, Online Courses) without reloading | 2 | Jannat | 30 | 2 | 31 | 2 | 100%
2,5,4 | Implement breadcrumbs to display navigation paths (e.g., Programs / Undergraduate / BSc in Computer Science) | 2 | Jannat | 32 | 1 | 33 | 1 | 100%
2,5,5 | Develop and link additional pages (Program Details) through Django views and URLs | 2 | Jannat | 33 | 1 | 34 | 2 | 100%
2,5,6 | Apply consistent responsive styling using pages.css and style.css for a cohesive design | 2 | Jannat | 34 | 2 | 36 | 2 | 100%
2,5,7 | Test and verify page loading, dynamic content navigation, and seamless flow through to ensure out all integrated elements | 2 | Jannat | 36 | 1 | 38 | 2 | 100%
2,6 | Create the user registration system #8 | 2 | Marcelo | 36 | 9 | 36 | 7 | 100%
2,6,1 | Set up of Authentication App inside Django, including Migrations and proper set up | 2 | Marcelo | 36 | 2 | 36 | 2 | 100%
2,6,2 | Creation of Administrator section and Superuser credentials | 2 | Marcelo | 38 | 1 | 38 | 1 | 100%
2,6,3 | Creation of Registration Form, along with UI changes and middleware set up | 2 | Marcelo | 39 | 2 | 39 | 2 | 100%
2,6,4 | Creation of Log In Form, along with UI changes and middleware set up | 2 | Marcelo | 41 | 2 | 41 | 1 | 100%
2,6,5 | Creation of Log Out Form, along with UI changes and middleware set up | 2 | Marcelo | 43 | 2 | 42 | 1 | 100%
3 | PROJECT PROGRESS REPORT | 2 | All group | 37 | 6 | 37 | 6 | 100%
3,1 | Progress Presentation #19 | 2 | All group | 37 | 3 | 37 | 3 | 100%
3,1,1 | Project Summary |  | All group | 37 | 3 | 37 | 3 | 100%
3,1,2 | Use Case diagram summarizing the features |  | All group | 37 | 3 | 37 | 3 | 100%
3,1,3 | Progress to Date |  | All group | 37 | 3 | 37 | 3 | 100%
3,1,4 | Challenges and Solutions |  | All group | 37 | 3 | 37 | 3 | 100%
3,1,5 | Next Steps |  | All group | 37 | 3 | 37 | 3 | 100%
3,2 | Progress Report #20 | 2 | All group | 40 | 3 | 40 | 3 | 100%
3,2,1 | Project Summary |  | All group | 40 | 3 | 40 | 3 | 100%
3,2,2 | Use Case diagram summarizing the features |  | All group | 40 | 3 | 40 | 3 | 100%
3,2,3 | Progress to Date |  | All group | 40 | 3 | 40 | 3 | 100%
3,2,4 | Challenges and Solutions |  | All group | 40 | 3 | 40 | 3 | 100%
3,2,5 | Next Steps |  | All group | 40 | 3 | 40 | 3 | 100%
4 | DEVELOPMENT AND INTEGRATION | 3 | All group | 39 | 46 | 39 |  | 30%
4,1 | Create the User Feedback System #12 | 3 | Nabil | 39 | 7 | 39 |  | 50%
4,1,1 | Set up the Django environment | 3 | Nabil | 39 | 0.5 | 39 |  | 0%
4,1,2 | Download and clone the existing project | 3 | Nabil | 39 | 0.5 | 39 |  | 0%
4,1,3 | Create the feedback input boxes utilizing Django forms | 3 | Nabil | 40 | 1 | 40 |  | 0%
4,1,4 | Connect to the database | 3 | Nabil | 41 | 1 | 41 |  | 0%
4,1,5 | Set up the feedback button in the navbar and match css styling to be consistent with the rest of the pages | 3 | Nabil | 42 | 2 | 42 |  | 0%
4,1,6 | Perform the unit and demo tests | 3 | Nabil | 44 | 2 | 44 |  | 0%
4,2 | Create chat transcript functionality for students #15 | 3 | Arnoldo | 41 | 5 | 41 | 5 | 100%
4,3 | Unit Test: Chatbot #16 | 3 | Jose | 41 | 6 | 41 | 6 | 100%
4,4 | Configure the project database #17 | 3 | Marcelo | 45 | 4 | 45 |  | 0%
4,4,1 | Create Program models | 3 | Marcelo | 45 | 1 | 45 |  | 0%
4,4,2 | Create User models | 3 | Marcelo | 46 | 1 | 46 |  | 0%
4,4,3 | Create signal to detect changes on users | 3 | Marcelo | 47 | 2 | 47 |  | 0%
4,5 | Create student enrollment system #18 | 3 | Marcelo | 47 | 16 | 47 |  | 0%
4,6 | Unit Test: Pages #27 | 3 | Selenge | 57 | 3 | 57 | 3 | 100%
4,7 | Unit Test: Users #28 | 3 | Arnoldo | 57 | 3 | 57 | 3 | 100%
4,8 | Convert Static Pages to Dynamic #30 | 3 | Afiya-Farjana | 63 | 1 | 63 |  | 0%
4,9 | Implement a professional development workflow #29 | 4 | Arnoldo | 58 | 15 | 58 |  | 0%
4,9,1 | Security & Secrets Management | 4 | Arnoldo | 58 | 4 | 58 |  | 0%
4,9,2 | Code Quality & Formatting | 4 | Arnoldo | 62 | 3 | 62 |  | 0%
4,9,3 | Pre-commit Hooks | 4 | Arnoldo | 65 | 2 | 65 |  | 0%
4,9,4 | CI Pipeline Integration | 4 | Arnoldo | 67 | 3 | 67 |  | 0%
4,9,5 | Architecture & Commit Standards | 4 | Arnoldo | 70 | 3 |  |  | 0%
4,10 | Create language switch #9 | 4 | Arnoldo | 61 | 10 | 61 |  | 50%
4,10,1 | Website Localization | 4 | Arnoldo | 61 | 5 | 61 | 5 | 100%
| Configure i18n in settings.py | 4 | Arnoldo | 61 | 1 | 61 | 1 | 100%
| Add LocaleMiddleware and update middleware order | 4 | Arnoldo | 62 | 0.5 | 62 | 0.5 | 100%
| Add language switch dropdown to navbar template | 4 | Arnoldo | 62 | 1 | 62 | 1 | 100%
| Use tags in all templates | 4 | Arnoldo | 63 | 1 | 63 | 1 | 100%
| Generate translation files | 4 | Arnoldo | 64 | 0.5 | 64 | 0.5 | 100%
| Translate English → Mongolian for static UI texts | 4 | Arnoldo | 65 | 1 | 65 | 1 | 100%
4,10,2 | Chatbot Localization | 4 | Arnoldo | 66 | 3 | 66 |  | 0%
| Read active language from cookie/session in chatbot endpoint | 4 | Arnoldo | 66 | 0.5 | 66 |  | 0%
| Implement language-aware rule-based chatbot logic | 4 | Arnoldo | 66 | 1 | 66 |  | 0%
| Add translation dictionary (MVP) for chatbot responses (English & Mongolian) | 4 | Arnoldo | 67 | 0.5 | 67 |  | 0%
| Return chatbot replies in the user’s selected language | 4 | Arnoldo | 67 | 0.5 | 67 |  | 0%
| Test chatbot responses in both languages | 4 | Arnoldo | 68 | 0.5 |  |  | 0%
4,10,3 | Testing | 4 | Arnoldo | 69 | 2 |  |  | 0%
| Verify language switch affects both website and chatbot | 4 | Arnoldo | 69 | 0.5 |  |  | 0%
| Write unit tests for language persistence and localized chatbot replies | 4 | Arnoldo | 70 | 0.5 |  |  | 0%
| Prepare demo steps and update documentation | 4 | Arnoldo | 70 | 0.5 |  |  | 0%
4,11 | Creating automatic resource delivery after registration #14 | 4 | Arnoldo | 70 | 3 | 70 |  | 0%
4,11,1 | Add email field to user registration form using a custom UserRegistrationForm | 4 | Arnoldo | 58 | 0.5 |  |  | 0%
4,11,2 | Update registration view to use the new form and validate email | 4 | Arnoldo | 58 | 0.5 |  |  | 0%
4,11,3 | Implement helper function to send welcome + admission resources email | 4 | Arnoldo | 59 | 0.5 |  |  | 0%
4,11,4 | Integrate email sending logic into the registration flow (trigger after successful registration) | 4 | Arnoldo | 59 | 0.5 |  |  | 0%
4,11,5 | Configure SMTP email backend using .env (Ethereal for dev) | 4 | Arnoldo | 60 | 0.5 |  |  | 0%
4,11,6 | Test email delivery + update E2E test to support new email field in registration flow | 4 | Arnoldo | 60 | 0.5 |  |  | 0%
4,12 | Unit test : Resource delivery #31 | 4 | Selenge | 73 | 3 |  |  | 0%
4,13 | Unit test: Localization #32 | 4 | Selenge | 73 | 3 |  |  | 0%
4,14 | Unit test: Feedback #33 | 4 | Selenge | 73 | 3 |  |  | 0%
4,15 | Send program resources via email upon request to the chatbot #35 | 4 | Selenge | 73 | 3 |  |  | 0%
4,15,1 | Create logic so that the student can navigate the chatbot to the email delivery option | 4 | Selenge | 67 | 0.5 |  |  | 0%
4,15,2 | Create email delivery logic on the Console Backend SMTP as a first test | 4 | Selenge | 67 | 0.5 |  |  | 0%
4,15,3 | Replace the console backend information with a SMTP mailbox sandbox service (ethereal.emai) | 4 | Selenge | 68 | 1 |  |  | 0%
4,15,4 | Ensure that no secret keys are exposed | 4 | Selenge | 69 | 1 |  |  | 0%
5 | BUG FIXING | 5 |  | 78 | 7 |  |  | 0%
6 | REPORT | 5 | All group | 78 | 7 |  |  | 0%
0%